## dashebord
Project Progress of Foreign Funded Projects - 2021
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## DATABASE
NO | PRO | Component | Total Estimate Cost | Allocation | Financial TQ 03 | Expenditure Q 03 | Cumulative Expenditure | Target Quarter 03 | Achievement (%)
1 | GCWMPI | Condition Assessment of 125 Km sewer | 14657 | 1400 | 440 | 244.35 | 13911.57 | 98.25% | 97.55%
2 | GCWMPI | Rehabilitation of Pumping Stations |  |  | 1250 | 199.26 |  | 87% | 76.76%
3 | GCWMPI | Individual Consultants |  |  | 40.5 | 21.86 |  | - | -
4 | GCWMPI | Training and Capacity development |  |  | 8 |  |  | - | -
5 | GCWMPI | Project Administration |  |  | 18.9 | 6.9 |  | - | -
6 | GCWWMPII | Support of Design, Supervision and Institutional Development | 1396 | 786 | 83 | 48.54 | 451 | 69.34% | 56.68%
7 | GCWWMPII | Sewer Cleaning, CCTV Investigation for the 108km of sewers |  |  | 326.21 | - |  | 20.5% | -
8 | GCWWMPIII | Construction supervision of kirulapana sewer | 26953 | 2000 | 1981.15 | 373.39 | 4494.9 | 72% | 61%
9 | GCWWMPIII | Construction of wastewater treatment plant - wellawatta |  |  | 1040.93 |  |  | 21% | 4%
10 | GCWWMPIII | Provide swerage facilities kirula - Narahenpita |  |  | 1155.6 |  |  | 1.4% | -
11 | GCWWMPIII | Repaire & defective sewer-sourthern catchment |  |  | 1013.4 |  |  | 1.4% | -
12 | GCWWMPIII | Goods & work |  |  | 10 |  |  | - | -
13 | GCWWMPIII | Project Management |  |  | 1 | 1.7 |  | - | -
14 | GCWWMPIII | Training |  |  | 7 |  |  | -
15 | GCWWMPIII | Administration & Resettlement Activities |  |  | 60.3 | 76.6 | 31.37 | - | -
16 | PSSP | Primary healthcare System Strengthening Project | 23843 | 3000 | 1800 | 1395 | 4607.4 | 35% | 27%
17 | Rural Bridges-II | Construction of 868 Rural Bridges | 34100 | 2100 | 2050 | 766.8 | 33179.17 | 100% | 97%
18 | Rural Bridges-III | Construction of 720 Rural Bridges | 27000 | 1500 | 1150 | 517.99 | 27221.77 | 100% | 98%
19 | Rural Bridges-V | Construction of 200 bridges - Phase 5 | 12400 | 2650 | 2200 | 2190 | 2190 | - | -
20 | RIDEP | Rural Road Construction | 20622 | 2010 | 1296.5 | 1696.94 | 3212 | 15% | 12%
21 | RIDEP | Construction of Water Supply |  |  | 385.07 |  |  | 8% | 5%
22 | RIDEP | Construction Irrigation |  |  | 338.03 |  |  | 6% | 6%
23 | RIDEP | Project Administration & Preperatory works |  |  | 1347.93 |  |  | 5% | 4%
24 | LDSP | Updating of 134 Local Authority Participatory Development Plans | 14915.71 | 4100 | 2883.8 | 317 | 660 | 50% | 100%
25 | LDSP | Training and Workshop | [5 empty] | 100% | 90%
26 | LDSP | Esteblishment of Social Audit Committees | [5 empty] | 100% | 100%
27 | LDSP | Preparation Business Plans | [5 empty] | 100% | 100%
28 | LDSP | Implementation of 368 local services improvement sub projects | [5 empty] | 75% | 45%
29 | LDSP | Providing Perfomance Grant | [5 empty] | 50% | 30%
30 | LDSP | TOT for SLILG, MDTU, LLDF and National/Provincial staff | [5 empty] | 45% | 25%
31 | LDSP | Technical Assistance to SMPCLGA | [5 empty] | 75% | 50%
32 | LDSP | Strengthening of GGRCs and Provincial Planning for planning and M&E | [5 empty] | 75% | 50%
33 | LDSP | Computerirization of Accounting Software, Capacity Building & Rollout of the new accounting System | [5 empty] | 75% | 50%
34 | GEM | General Education for Modernization | 15505 | 2000 | 1350 | 904.5 | 1304.5 | 15% | 0%
35 | Puraneguma | 1. Water Supply Projects | 12010 | 2500 | 2100 | 1959.35 | 8204.32 | 79% | 71%
36 | Puraneguma | 2. PS Buildings | [5 empty] | 100% | 99%
37 | Puraneguma | 3. Public Market | [5 empty] | 100% | 98%
38 | Puraneguma | 4. Health Centers | [5 empty] | 100% | 93%
39 | Puraneguma | 5. Libraries | [5 empty] | 100% | 100%
40 | Puraneguma | 6. Auditorium | [5 empty] | 100% | 99%
41 | Puraneguma | 7. Crematorium | [5 empty] | 100% | 98%
42 | Puraneguma | 8. Weeklyfair | [5 empty] | 100% | 100%
43 | Puraneguma | 9. Procurement of Goods | [5 empty] | 100% | 100%
44 | Fire Fighting | Establishment of Fire Fighting units - CMC | 2038 | 1230 | 1230 | 1948.5 | 2422.44 | 100% | 90%
45 | TCAMP | Construction of 39 Road packages | 15020 | 3150 | 6055.95 | 2724.6 | 3872.55 | 59.5% | 41.23%

## TEC
Row Labels | Sum of Total Estimate Cost | Sum of Cumulative Expenditure
TCAMP | 15020 | 3872.55
Grand Total | 15020 | 3872.55

## Allocation
Row Labels | Sum of Allocation | Sum of Expenditure Q 03
TCAMP | 3150 | 2724.6
Grand Total | 3150 | 2724.6

## Financil_Progress
Row Labels | Sum of Financial TQ 03 | Sum of Expenditure Q 03
TCAMP | 6055.95 | 2724.6
Grand Total | 6055.95 | 2724.6

## Physical
Row Labels | Sum of Target Quarter 03 | Achievement
Construction of 39 Road packages | 0.595 | 0.4123
Grand Total | 0.595 | 0.4123

## Sheet4
NO | PRO | Component | Total Estimate Cost | Allocation | Financial_TQ2 | ExpenditureQ2 | Cumulative Expenditure | Target_Quarter | Achievement (%)
39 | GCWMPI | Interest and Commitment Chargers |  | 80 | 40 | 52.88 |  | 0 | 0
38 | GCWMPI | Project Administration |  | 24 | 12 | 22.06 |  | 0 | 0
37 | GCWMPI | Training and Capacity development |  | 42.4 | 22.2 | 0.26 |  | 0 | 0
36 | GCWMPI | Individual Consultants |  | 61.6 | 30.8 | 16.57 |  | 0 | 0
35 | GCWMPI | Rehabilitation of CS19 sewer / wannathamulla sewer |  | 150 | 60 | 0 |  | 0.16 | 0
34 | GCWMPI | Rehabilitation of Pumping Stations |  | 2580 | 1290 | 351.37 |  | 0.65 | 0.416
33 | GCWMPI | Condition Assessment of sewer |  | 895 | 586 | 216.36 |  | 0.997 | 0.9619