## dashebord
Project Progress of Foreign Funded Projects - 2021
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## DATABASE
NO | PRO | Location | Component | Total Estimate Cost | Allocation | Financial TQ 03 | Expenditure Q 03 | Cumulative Expenditure | Target Quarter 03 | Achievement (%)
1 | GCWMPI | CMC Area, Colombo District | Condition Assessment of 125 Km sewer | 14657 | 1400 | 440 | 297.4 | 13987.43 | 98.25% | 98.69%
2 | GCWMPI |  | Rehabilitation of Pumping Stations |  |  | 1250 | 201.87 |  | 87% | 76.84%
3 | GCWMPI |  | Individual Consultants |  |  | 40.5 | 32.67 |  | - | -
4 | GCWMPI |  | Training and Capacity development |  |  | 8 | - |  | - | -
5 | GCWMPI |  | Project Administration |  |  | 18.9 | 6.9 |  | - | -
6 | GCWWMPII |  | Support of Design, Supervision and Institutional Development | 1396 | 786 | 83 | 69.9 | 471.9 | 69.34% | 57.16%
7 | GCWWMPII |  | Sewer Cleaning, CCTV Investigation for the 108km of sewers |  |  | 326.21 | - |  | 20.5% | -
8 | GCWWMPIII |  | Construction supervision of kirulapana sewer | 26953 | 2000 | 1981.15 | 614.98 | 4598.83 | 72% | 63%
9 | GCWWMPIII |  | Construction of wastewater treatment plant - wellawatta |  |  | 1040.93 |  |  | 21% | 6%
10 | GCWWMPIII |  | Provide swerage facilities kirula - Narahenpita |  |  | 1155.6 |  |  | 1.4% | -
11 | GCWWMPIII |  | Repaire & defective sewer-sourthern catchment |  |  | 1013.4 |  |  | 1.4% | -
12 | GCWWMPIII |  | Goods & work |  |  | 10 |  |  | - | -
13 | GCWWMPIII |  | Project Management |  |  | 1 | 7.23 |  | - | -
14 | GCWWMPIII |  | Training |  |  | 7 | - |  | -
15 | GCWWMPIII |  | Administration & Resettlement Activities |  |  | 60.3 | 98.62 | 31.37 | - | -
16 | PSSP | All 25 District | New Constructions - 714 Sub Projects | 23843 | 3000 | 1800 | 1445 | 4660 | 12% | 9%
| PSSP |  | Renovation - 711 Sub Projects | [5 empty] | 19% | 13%
| PSSP |  | Improvement and Upgrading - 707 Sub Projects | [5 empty] | 25% | 20%
| PSSP |  | Essential Medical Equipment - 698 Sup Projects | [5 empty] | 36% | 29%
| PSSP |  | Non Medical Equipment - 569 Sub Projects | [5 empty] | 30% | 20%
| PSSP |  | Awareness Programme - 697 Sub Projects | [5 empty] | 31% | 27%
| PSSP |  | Training amd Capasity Building - 754 Sub Projects | [5 empty] | 24% | 19%
| PSSP |  | IT equipment and Installation of IT infrastructure - 532 Sub Projects | [5 empty] | 26% | 19%
| PSSP |  | Purchasing of 65 Vehicles | [5 empty] | 15% | 8%
| PSSP |  | Other Subprojects | [5 empty] | 44% | 40%
17 | Rural Bridges-II | All 25 District | Construction of 868 Rural Bridges | 34100 | 2100 | 2050 | 775.51 | 33187.88 | 100% | 98%
18 | Rural Bridges-III |  | Construction of 720 Rural Bridges | 27000 | 1500 | 1150 | 552.51 | 27256.23 | 100% | 98%
19 | Rural Bridges-V |  | Construction of 200 bridges - Phase 5 | 12400 | 2650 | 2200 | 2546.3 | 2546.3 | - | -
20 | RIDEP | All District of Northern, Eastern, North Central & Uva Province | Rural Road Construction | 20622 | 2010 | 1296.5 | 1775.03 | 3290.1 | 15% | 11%
21 | RIDEP |  | Construction of Water Supply |  |  | 385.07 |  |  | 8% | 4%
22 | RIDEP |  | Construction Irrigation |  |  | 338.03 |  |  | 6% | 4.5%
23 | RIDEP |  | Project Administration & Preperatory works |  |  | 1347.93 |  |  | 5% | 4.25%
24 | LDSP | All District of Northern, Eastern, North Central & Uva Province | Updating of 134 Local Authority Participatory Development Plans | 14915.71 | 4100 | 2883.8 | 308.96 | 693 | 100% | 100%
25 | LDSP |  | Training and Workshop | [5 empty] | 100% | 90%
26 | LDSP |  | Esteblishment of Social Audit Committees | [5 empty] | 100% | 80%
27 | LDSP |  | Preparation Business Plans | [5 empty] | 100% | 100%
28 | LDSP |  | Implementation of 368 local services improvement sub projects | [5 empty] | 75% | 51%
29 | LDSP |  | Providing Perfomance Grant | [5 empty] | 50% | -
30 | LDSP |  | TOT for SLILG, MDTU, LLDF and National/Provincial staff | [5 empty] | 45% | 25%
31 | LDSP |  | Technical Assistance to SMPCLGA | [5 empty] | 75% | 40%
32 | LDSP |  | Strengthening of GGRCs and Provincial Planning for planning and M&E | [5 empty] | 75% | 40%
33 | LDSP |  | Computerirization of Accounting Software, Capacity Building & Rollout of the new accounting System | [5 empty] | 75% | 40%
34 | GEM | All 25 District | General Education for Modernization | 15505 | 2000 | 1350 | 905 | 1305 | 15% | 0%
35 | Puraneguma | Western, Southern, Central, uva, North Western, North and Central Provinces | 1. Water Supply Projects | 12010 | 2500 | 2100 | 2111.15 | 8356.12 | 79% | 72%
36 | Puraneguma |  | 2. PS Buildings | [5 empty] | 100% | 99%
37 | Puraneguma |  | 3. Public Market | [5 empty] | 100% | 99%
38 | Puraneguma |  | 4. Health Centers | [5 empty] | 100% | 94%
39 | Puraneguma |  | 5. Libraries | [5 empty] | 100% | 100%
40 | Puraneguma |  | 6. Auditorium | [5 empty] | 100% | 99%
41 | Puraneguma |  | 7. Crematorium | [5 empty] | 100% | 100%
42 | Puraneguma |  | 8. Weeklyfair | [5 empty] | 100% | 100%
43 | Puraneguma |  | 9. Procurement of Goods | [5 empty] | 100% | 100%
44 | Fire Fighting | CMC Area, Colombo District | Establishment of Fire Fighting units - CMC | 2038 | 1230 | 1230 | 1948.5 | 2422.44 | 100% | 95%
45 | TCAMP | All 25 District | Construction of 39 Road packages | 15020 | 3150 | 6055.95 | 3069.89 | 4217.89 | 59.5% | 41.23%

## TEC
Row Labels | Sum of Total Estimate Cost | Sum of Cumulative Expenditure
GEM | 15505 | 1305
Grand Total | 15505 | 1305

## Allocation
Row Labels | Sum of Allocation | Sum of Expenditure Q 03
GEM | 2000 | 905
Grand Total | 2000 | 905

## Financil_Progress
Row Labels | Sum of Financial TQ 03 | Sum of Expenditure Q 03
GEM | 1350 | 905
Grand Total | 1350 | 905

## Physical
Row Labels | Sum of Target Quarter 03 | Achievement
General Education for Modernization | 0.15 | 0
Grand Total | 0.15 | 0

## Sheet4
NO | PRO | Component | Total Estimate Cost | Allocation | Financial_TQ2 | ExpenditureQ2 | Cumulative Expenditure | Target_Quarter | Achievement (%)
39 | GCWMPI | Interest and Commitment Chargers |  | 80 | 40 | 52.88 |  | 0 | 0
38 | GCWMPI | Project Administration |  | 24 | 12 | 22.06 |  | 0 | 0
37 | GCWMPI | Training and Capacity development |  | 42.4 | 22.2 | 0.26 |  | 0 | 0
36 | GCWMPI | Individual Consultants |  | 61.6 | 30.8 | 16.57 |  | 0 | 0
35 | GCWMPI | Rehabilitation of CS19 sewer / wannathamulla sewer |  | 150 | 60 | 0 |  | 0.16 | 0
34 | GCWMPI | Rehabilitation of Pumping Stations |  | 2580 | 1290 | 351.37 |  | 0.65 | 0.416
33 | GCWMPI | Condition Assessment of sewer |  | 895 | 586 | 216.36 |  | 0.997 | 0.9619