## Sheet1
NO | PRO | Component | Sub Components | Overall Target | Overall Achivement | Target Quarter 01 | Achievement (%)
16 | Puraneguma | Water Supply Projects - Completed | Ibbagamuwa WS |  |  | 1 | 1

## dashebord
Project Progress of Foreign Funded Projects - 2021
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## DATABASE
NO | PRO | Component | Sub Components | Overall Target | Overall Achivement | Target Quarter | Achievement (%)
1 | GCWMPI | Rehabilitation of Pumping Stations | Wannthamulla PS | 82% | 76.76% | 100% | 96.7%
2 | GCWMPI | Rehabilitation of Pumping Stations | Maligawatta PS |  |  | 100% | 74.81%
3 | GCWMPI | Rehabilitation of Pumping Stations | Vystwyke PS |  |  | 100% | 70.81%
4 | GCWMPI | Rehabilitation of Pumping Stations | Bambalapitiya PS |  |  | 100% | 99.7%
5 | GCWMPI | Rehabilitation of Pumping Stations | Thibirigasyaya PS |  |  | 100% | 72.59%
6 | GCWMPI | Rehabilitation of Pumping Stations | Slave Island |  |  | 100% | 96.64%
7 | GCWMPI | Rehabilitation of Pumping Stations | Borella |  |  | 100% | 61.2%
8 | GCWMPI | Rehabilitation of Pumping Stations | CS3 |  |  | 100% | 99.79%
9 | GCWMPI | Rehabilitation of Pumping Stations | Central Monitoring System |  |  | 100% | 78.16%
10 | GCWMPI | Rehabilitation of Pumping Stations | Drainage Division Workshop |  |  | 100% | 100%
11 | Puraneguma | 1. Water Supply Projects - Completed | Extention to Thambalawewa extentions in Bandiwewa Water Supply Scheme in Polonnaruwa District. | 79% | 71% | 100% | 100%
12 | Puraneguma | 3. Treatment Plant - Completed | Minneriya Water treatment Plant Improvement Project (Construction of Rapid Sand Filter) |  |  | 100% | 100%
13 | Puraneguma | 1. Water Supply Projects - Completed | Extension of Water Supply Scheme of Thambala in Polonnaruwa District |  |  | 100% | 100%
14 | Puraneguma | 1. Water Supply Projects - Completed | Extention to Uththupitiya (From Kekirawa Water Supply Scheme) in Anuradhapura District |  |  | 100% | 100%
15 | Puraneguma | 1. Water Supply Projects - Completed | Extention to Mahailuppallama and Thirappane in Anuradhapura District |  |  | 100% | 100%
16 | Puraneguma | 1. Water Supply Projects - Completed | Extentions to Elagamuwa Main and Distribution System in Anuradhapura District |  |  | 100% | 100%
17 | Puraneguma | 1. Water Supply Projects - Completed | Improvements to Kebithigollewa Water Supply Scheme, NCP |  |  | 100% | 100%
18 | Puraneguma | 1. Water Supply Projects - Completed | Rajanganaya, Namalgamuwa and Kandegama in Anuradhapura District |  |  | 100% | 100%
19 | Puraneguma | 1. Water Supply Projects - Completed | Extention to Ibbagamuwa, (Pipe Network) North Western Province |  |  | 100% | 100%
20 | Puraneguma | 1. Water Supply Projects - Completed | Ibbagamuwa Water Supply Scheme |  |  | 100% | 100%
21 | Puraneguma | 1. Water Supply Projects - Completed | Rideemaliyadda (at Kuralawela, Ekiriyankumbura) |  |  | 100% | 100%
| Puraneguma | 1. Water Supply Projects - Completed | Rahathangama, Kumaragama and Kukurampola (From Buttala Water Supply Scheme) |  |  | 100% | 100%
22 | Puraneguma | 2. Water Supply - Ongoing | Rahathangama (From Buttala Water Supply Scheme) |  |  | 100% | 59%
23 | Puraneguma | 1. Water Supply Projects - Completed | Renovation and Augmentation of existing Water Treatment Plant at Dambulla |  |  | 100% | 100%
24 | Puraneguma | 2. Water Supply - Ongoing | Sewagama Water Tower | 79% | 71% | 100% | 97%
25 | Puraneguma | 2. Water Supply - Ongoing | Nikaweratiya-Ambanpola |  |  | 100% | 96%
26 | Puraneguma | 2. Water Supply - Ongoing | Karuwalagaswewa Pradeshiya Sabha |  |  | 90% | 52%
27 | Puraneguma | 2. Water Supply - Ongoing | Bathalayaya and Belaganwewa Areas |  |  | 100% | 74%
28 | Puraneguma | 2. Water Supply - Ongoing | Passara Water Supply Scheme |  |  | 100% | 42%
29 | Puraneguma | 2. Water Supply - Ongoing | Dambulla Rural Areas and Kandalama |  |  | 81% | 64%
30 | Puraneguma | 2. Water Supply - Ongoing | Inamaluwa and Kithulhitiyawa |  |  | 97% | 92%
31 | Puraneguma | 2. Water Supply - Ongoing | Sigiriya and Habarana |  |  | 98% | 93%
32 | Puraneguma | 2. Water Supply - Ongoing | Galewela and Tiththawelgolla |  |  | 85% | 78%
33 | Puraneguma | 2. Water Supply - Ongoing | Pahaladiggala |  |  | 60% | 50%
34 | Puraneguma | 2. Water Supply - Ongoing | Udapalatha, Udadumbara and Wilgamuwa PS Areas |  |  | 80% | 74%
35 | Puraneguma | 2. Water Supply - Ongoing | Kuruswatta, Nattandiya Pradeshiya Sabha |  |  | 100% | 96%
36 | Puraneguma | 2. Water Supply - Ongoing | Water Bowsers NWP |  |  | 100% | 100%
37 | Puraneguma | 2. Water Supply - Ongoing | Water supplyng distribution network in Minneriya (Galoya-GN division) |  |  | - | -
38 | Puraneguma | 3. Treatment Plant - Completed | Minneriya Treatment Plant in NCP | 79% | 71% | 100% | 100%
39 | Puraneguma | 3. Treatment Plant - Ongoing | Nuwarawewa Water Treatment Plant, North Central Province |  |  | 100% | 99%
40 | Puraneguma | 3. Treatment Plant - Ongoing | Kalawewa Treatment Plant, NCP |  |  | 100% | 83%
41 | Puraneguma | 3. Treatment Plant - Ongoing | Augmentation of Girandurukotte Treatment Plant |  |  | 80% | 47%
42 | Puraneguma | 3. Treatment Plant - Ongoing | Augmentation of Girandurukotte Treatment Plant |  |  | 65% | 9.5%
43 | Puraneguma | 3. Treatment Plant - Ongoing | Tissawewa Treatment Plant, NCP |  |  | - | -
44 | Puraneguma | 4. PS Buildings - Completed | Nanu Oya - Nuwara Eliya Pradeshiya Sabha | 100% | 99% | 100% | 100%
45 | Puraneguma | 4. PS Buildings - Completed | Pallepola Pradeshiya Sabha |  |  | 100% | 100%
46 | Puraneguma | 4. PS Buildings - Completed | For Kurunegala Pradeshiya Sabha |  |  | 100% | 100%
47 | Puraneguma | 4. PS Buildings - Completed | Netolpitiya for Tangalle Pradeshiya Sabha |  |  | 100% | 100%
48 | Puraneguma | 4. PS Buildings - Completed | Habaraduwa Pradeshiya Sabha |  |  | 100% | 100%
49 | Puraneguma | 4. PS Buildings - Completed | Nayagoda for Rathgama Pradeshiya Sabha |  |  | 100% | 100%
50 | Puraneguma | 4. PS Buildings - Completed | Baddegama |  |  | 100% | 100%
51 | Puraneguma | 4. PS Buildings - Completed | Bentota Pradeshiya Sabha |  |  | 100% | 100%
52 | Puraneguma | 4. PS Buildings - Completed | Pahala Karagahamuna for Mahara PS - Stage 1 |  |  | 100% | 100%
53 | Puraneguma | 4. PS Buildings - Completed | Waskaduwa Town for Kalutara PS-Stage 1 |  |  | 100% | 100%
54 | Puraneguma | 4. PS Buildings - Completed | Kandana for Ja-Ela PS - Stage 1 |  |  | 100% | 100%
55 | Puraneguma | 4. PS Buildings - Completed | Mahabage for Wattala PS |  |  | 100% | 100%
56 | Puraneguma | 4. PS Buildings - Completed | Beruwala Pradeshiya Sabha - stage 1 |  |  | 100% | 100%
57 | Puraneguma | 5. PS Buildings - Ongoing | For Narammala Pradeshiya Sabha |  |  | 100% | 98%
58 | Puraneguma | 4. PS Buildings - Completed | Southern Province (Ambalangoda, Baddegama, Habaraduwa, Ratgama, Tangalla and Matara PSs | 100% | 99% | 100% | 100%
59 | Puraneguma | Health Centres | Matale Pradeshiya Sabha | 100% | 93% | 100% | 100%
60 | Puraneguma | Health Centres | Mahawatta for Kundasale Pradeshiya Sabha |  |  | 100% | 100%
61 | Puraneguma | Health Centres | Polgolla for Kundasale PS |  |  | 100% | 100%
62 | Puraneguma | Health Centres | Udunuwara for Pradeshiya Sabha |  |  | 100% | 100%
63 | Puraneguma | Health Centres | Nahena for Kelaniya Pradeshiya Sabha |  |  | 85% | 64%
64 | Puraneguma | Public Market | Gelioya for Udunuwara Pradeshiya Sabha | 100% | 98% | 100% | 100%
65 | Puraneguma | Public Market | Polgahawela for Polgahawela Pradeshiya Sabha |  |  | 100% | 98%
66 | Puraneguma | Public Market | Madurankuliya for Puttalam Pradeshiya Sabha |  |  | 100% | 100%
67 | Puraneguma | Public Market | Balapitiya Pradeshiya Sabha |  |  | 100% | 100%
68 | Puraneguma | Public Market | Kekandura for Matara Pradeshiya Sabha - SP |  |  | 100% | 100%
69 | Puraneguma | Public Market | Homagama Pradeshiya Sabha - Stage 1 |  |  | 100% | 100%
70 | Puraneguma | Public Market | Wadduwa for Panadura Pradeshiya Sabha |  |  | 100% | 88%
71 | Puraneguma | Library | Dunkannawa for Naththandiya Pradeshiya Sabha | 100% | 100% | 100% | 100%
72 | Puraneguma | Library | Madurankuliya for Puttalam Pradeshiya Sabha |  |  | 100% | 100%
73 | Puraneguma | Weekly Fair | Gonagala for Bentota Pradeshiya Sabha | 100% | 100% | 100% | 100%
74 | Puraneguma | Auditorium | Batapola for Ambalangoda Pradeshiya Sabha | 100% | 99% | 100% | 100%
75 | Puraneguma | Auditorium | Kadirana for Katana PS |  |  | 100% | 99%
76 | Puraneguma | Crematorium | Warakapitiya for Weligama Pradeshiya Sabha | 100% | 98% | 100% | 98%
77 | TCAMP-PRDP | 1. Phase I Stage I | WP/01 Mahagama Pannipitya Rd 1.2km Udahamulla Madiwela Rd 2.00km Kottawa Athurugiriya Rd 5.55km Niyadagala Dolekade Rd 2.96km | 60% | 41.23% | 100% | 56%
78 | TCAMP-PRDP | 1. Phase I Stage I | WP/02 Watareka Beruketiya Rd 8.25km Munagama Millawa Rd 7.25km | - | - | 100% | 95%
79 | TCAMP-PRDP | 1. Phase I Stage I | SP/01 Yatalamattta Udugama Rd 3.00km Wijayananda Mawatha Rd 4.20km Rathgama Sandarawala Rd 6.30km Ovilana Pitadeniya Rd 5.40km | - | - | 100% | 98%
80 | TCAMP-PRDP | 1. Phase I Stage I | SP/02 Kadduwa Thibbatuwawa Rd 7.60km Weraduwa Aparekka Rd 1.00km Gandara Wataruma Rd 1.50km Deeyagaha Motagedara 3.10km Bandarawatta Mahawatta 2.80km | - | - | 100% | 51%
81 | TCAMP-PRDP | 1. Phase I Stage I | EP/01 Damana Ambalanoya Pannalagama Rd 23.00km Divulna Vellaveli Rd 3.20km Malwatta Suripodai Rd 5.10km | - | - | 100% | 35.41%
82 | TCAMP-PRDP | 1. Phase I Stage I | EP/02 New Boudary Rd 2.50km Kokuvil Sathurukondan Rd 4.60km Komariya Mandur Rd 7.00km | - | - | 100% | 49%
83 | TCAMP-PRDP | 1. Phase I Stage I | NWP/01 Yangalmodara Morawalpitiya Rd 3.95km Puhuriya Koswaththa Rd 3.50km Mallawapitiya - Katupitiya Rd 3.40km Kiriwavula Meegolla Rd 2.80km | - | - | 100% | 98%
84 | TCAMP-PRDP | 1. Phase I Stage I | NWP/02 Madurankuliya Mukkuthoduwawa 2.35km Kurinnampitiya Kandakuliya 3.50km Aluthgama Ihalapuliyankulama Rd 5.30km Anamaduwa Gamudawa Rd 1.60km Puttalam Outer Circular Rd 1.68km Kalpitiya Aniwasal Rd 1.00km | - | - | 75% | 22%
85 | TCAMP-PRDP | 2. Phase I Stage II | NCP/01 Oyamaduwa Pemaduwa Rd 10.22km Nochchiyagama Galewawa Rd 5.02km | 60% | 41.23% | 100% | 87%
86 | TCAMP-PRDP | 2. Phase I Stage II | NCP/02 D-2 Canel Bund Rd 2.80km Kothalawala Rd 5.56km Medirigiriya Ambagaswewa Rd 6.50km Aselapura Kurulubedda Rd 8.00km | - | - | 75% | 39%
87 | TCAMP-PRDP | 2. Phase I Stage II | UV/01 KodayanaWathtegama Rd 14.20km Hulandawa South Gamunupura Mahamewnawa Rd 2.00km | - | - | 55% | 43%
88 | TCAMP-PRDP | 2. Phase I Stage II | CP/01 Edaduwa Godagandeniya Rd 1.33km Godamuna Kithulpe Rd 3.86km Kuruduwatta Polmalgama Rd 1.75km Nikathanna Haragama Rd 2.75km Anangama Edaduwawa Rd 1.41km | - | - | 52% | 36%
89 | TCAMP-PRDP | 2. Phase I Stage II | CP/02 Makuruppu Lamasooriya Rd 5.00km Nildandahinna Galkatiwela Theripaha Rd 7.00km | - | - | 52% | 37%
90 | TCAMP-PRDP | 2. Phase I Stage II | NP/01 Vadaliyadaippu Maliwai Rd 4.20km Mavali Periyathurai Rd 3.65km Adiyapatham 1.95km Polikandy Navidil Karanavai Rd 3.55km Kaithady Junction to Kaithaday North 3.22km Chavakachcheri Nunavil Rd 2.04km | - | - | 50% | 18%
91 | TCAMP-PRDP | 2. Phase I Stage II | NP/02 Wilson Rd 2.50km Iyankachchi Kaththilaipalli 3.10km Pallikuda Fisheries Rd 2.81km Murasumaddi - Kokuvil Karrippadaimurippu Rd 2.00km Palai Thambigamam Rd 2.50km | - | - | 100% | 78%
92 | TCAMP-PRDP | 3. Phase II Stage I | WP/03 Kandalama Madurupitiya Rd 4.80km Muruthana Bambukuliya Rd 3.40km Adiambalama Kithulpitiya Rd 2.00km | 60% | 41% | 55% | 12%
93 | TCAMP-PRDP | 3. Phase II Stage I | NWP/03 Maho Nagollagama Rd 10.00km Maspotha Thisnapola Rd 4.20km | - | - | 55% | 65%
94 | TCAMP-PRDP | 3. Phase II Stage I | NCP/03 Dambuluhalmillewa Galkiriyagama Rd 11.00km Negama Halmillewa Rd 5.00km Rathmale Nachchaduwa Rd 3.00km Alisthna Thuruwila Rd 2.80km | - | - | 55% | 25%
95 | TCAMP-PRDP | 3. Phase II Stage I | UV/03 Ambagasdowa Dangamuwa Rd 4.44km Nugathalawa Jayasooriya Rd 5.03km | - | - | 55% | 12%
96 | TCAMP-PRDP | 3. Phase II Stage I | EP/04 Hensman Rd 6.00km Thumpankerney Thikkodai Rd 7.00km Police Station Eruvil Rd 1.44km Vavuvathivu Karaveddi Rd 2.00km | - | - | 55% | 10%
97 | TCAMP-PRDP | 3. Phase II Stage I | CP/03 Hettipola Town Rd 1.20km Hattota Amuna Colony Rd 2.20km Siyambalagaswewa (Nagolla -Welipitiya) Rd 4.00km Sigiriya Pidurangala Awudawela Rd 4.00km | - | - | 55% | 9%
98 | TCAMP-PRDP | 3. Phase II Stage I | NP/03R Pallamadhu Vidathalthivu Rd 1.77km Thiruketheswaram Rd 1.34km Puthukkuduyirippu Rd 1.80km Coolyshed rd 0.80km Erukkalampitty Amaipadukkai Rd 1.75km Nanattan Periyapulaveli Potkerney Rd 2.74km Nedunkandal Sornapuri Karukkakulam Rd 1.20km | - | - | 50% | 4%
99 | TCAMP-PRDP | 3. Phase II Stage I | SP/03R Narawela Poddala Rd 3.90km Ulukvitike Karapitiya Rd 0.56km Ukwaththa Piyadigama Rd 2.56km | - | - | 50% | -
100 | TCAMP-PRDP | 3. Phase II Stage I | EP/03R LB Chanel Rd 8.50km | - | - | - | -
101 | TCAMP-PRDP | 3. Phase II Stage I | UV/05R Ella Halpe Rd 2.17km Bindunuwewa Badulugasthenna Rd 2.43km Dikulpotha Kirioruwa Rd 3.10km Marangahawel Kosgama Rd 3.50km | - | - | - | -
102 | TCAMP-PRDP | 3. Phase II Stage I | SG/04R Niwithigala Kolombugama Rd 6.10km Warathalgoda Kelinkanda Rd 6.40km Morahela Ampitiya Rd 5.20km | - | - | 50% | 5%
103 | TCAMP-PRDP | 3. Phase II Stage I | SG/05R Dewala Junction Higgoda Ganthuna Rd 4.00km Yatideriya Uduwa Suriyamalgama Rd 2.10km Udukumbura Othanapitiya Rd 5.85km | - | - | 50% | 5%

## TEC
Row Labels
GCWMPI
Grand Total

## Allocation
Row Labels
GCWMPI
Grand Total

## Financil_Progress
Row Labels | Sum of Overall Target | Sum of Overall Achivement
GCWMPI | 0.82 | 0.7676
Grand Total | 0.82 | 0.7676

## Physical
Row Labels | Sum of target Quarter | Achievement
Bambalapitiya PS | 1 | 0.997
Borella | 1 | 0.612
Central Monitoring System | 1 | 0.7816
CS3 | 1 | 0.9979
Drainage Division Workshop | 1 | 1
Maligawatta PS | 1 | 0.7481
Slave Island | 1 | 0.9664
Thibirigasyaya PS | 1 | 0.7259
Vystwyke PS | 1 | 0.7081
Wannthamulla PS | 1 | 0.967
Grand Total | 10 | 8.504

## Sheet4
NO | PRO | Component | Total Estimate Cost | Allocation | Financial_TQ2 | ExpenditureQ2 | Cumulative Expenditure | Target_Quarter | Achievement (%)
39 | GCWMPI | Interest and Commitment Chargers |  | 80 | 40 | 52.88 |  | 0 | 0
38 | GCWMPI | Project Administration |  | 24 | 12 | 22.06 |  | 0 | 0
37 | GCWMPI | Training and Capacity development |  | 42.4 | 22.2 | 0.26 |  | 0 | 0
36 | GCWMPI | Individual Consultants |  | 61.6 | 30.8 | 16.57 |  | 0 | 0
35 | GCWMPI | Rehabilitation of CS19 sewer / wannathamulla sewer |  | 150 | 60 | 0 |  | 0.16 | 0
34 | GCWMPI | Rehabilitation of Pumping Stations |  | 2580 | 1290 | 351.37 |  | 0.65 | 0.416
33 | GCWMPI | Condition Assessment of sewer |  | 895 | 586 | 216.36 |  | 0.997 | 0.9619